## Model Tache
Tâche | Type | Date d'échéance | Etat d'avancement
2-2-1 Modelling & simulation | Etude | 2025-11-28 | 75%
2-2-5 Industrial feasability | Etude | 2025-10-23 | 100%
2-2-6_AMDEC Product | Etude | 2025-10-31 | 100%
2-2-7 Drafting of validation plan | Etude | 2025-11-28 | 50%
2-2-8_Preliminary design validation - PDR | Etude | 2025-10-31 | 100%
2-3-1 Mechanical sizing | Etude | 2025-11-28 | 75%
2-3-2 Detail design | Etude | 2025-11-28 | 75%
2-3-3 Prototype tooling and testing | Etude | 2025-11-28 | 25%
2-3-4 Design validation - CDR | Etude | 2026-01-09 | 0%